Making it Real : Sample action plan

The sample action plan below provides a guide to the approach that could be taken when developing a Making it Real action plan. However, many organisations will have their own business planning processes and frameworks and it makes sense to use these where they are in place.

The main recommendations we would make would be to:

1. Ensure the action plan is easy to understand (so that a member of the public can understand it)

2. Do not use any jargon or acronyms (apart from initials of names where you do not want these to be public)

3. Have high aspirations, but ensure they are measurable and realistic.

4. Keep linking the actions back to Making it Real

| Priority 1: People - Improve two way communication with people who use services and carers |
| --- |
| Action | Lead contact | Expected result | User/carer involvement | Deadline |
| Co-produce user/carer involvement questionnaire with user/carer group and Senior Leadership team | MC | Questionnaire produced | Intensive involvement of 3 to 4 people who use services/carers | April 2012 |
| Identify teams who will achieve most benefits from co-production with users. | DR | Teams understand level and quality of existing user/carer involvement | Intensive involvement of 3 to 4 people who use services and carers | May 2012 |
| Develop action plan for selected teams | DR | Teams have clear focus for specific co-production activities | Involvement of wider user/carer groups. | June 2012 |
| Increase capacity of existing user/carer and citizens groups | MC | User/carer group is more diverse, more flexible membership | Involvement of wider user/carer groups | June 2012 |
| Commission online facility for user/carer feedback – link to Making it Real website pages. | DR | Two way feedback from users/carers ensures MIR is carefully monitored | Available to wider public. | Commission in April 2012 Complete Sept 2012 |

| Priority 2 : Workforce - Build Making it Real themes into staff leadership training programmes. |
| --- |
| Action | Lead contact | Expected result | User/carer involvement | Deadline |
| Evaluate staff training programmes to test whether existing training supports the move towards more personalised and community based support. | SB | Understanding of how training impacts on staff culture – will help to identify what is working well/ what can be improved. | Intensive involvement of 6 people who use services/carers with specific interest in staff training. | Commission April 2012 Complete Sept 2012 |
| Analyse results of evaluation and develop a framework for new training. | SB | New training framework incorporates recommendations of evaluation. |  | November 2012 |
| Test and improve new training programme with selected staff teams. | SB | Improved training programme leads to improved user/carer satisfaction. | Greater involvement of people who use services in training staff | Jan to March 2013 |

| Priority 3: Working with Partners –Encourage the development of organisations who support independent living |
| --- |
| Action | Lead contact | Expected result | User/carer involvement | Deadline |
| Organise 4 partner events (including people who use services, community organisations, User Led Organisations and commissioners) to identify how we can offer sustainable support for Independent living | KR | Open and transparent debate about the best ways that sustainable support can be developed. | The whole process is co-produced with people who use services, carers and local citizens. | April to July 2012 |
| Develop a clear strategy explaining how we will support the development of Independent Living in our area. | KR | Open and transparent debate about the best ways that sustainable support can be developed. | The whole process is co-produced with people who use services, carers and local citizens. | Sept 2012 |
| Identify funding and support for Independent Living strategy to ensure we can build on the existing expertise in the locality. | KR | Commissioners and Senior managers agree a sustainable funding programme. | Involvement of 3 to 4 user/carer representatives. | Sept 2012 |